## Sheet1
WBS Keypoints - Extend 'Videos' Post Type For Programatic Access through API
S.No. | Task Name | Task Details | Efforts | Theme Support | WordPress Support | API Type | Query: ask from client
1 | Create/Register End points for Video Content type | 24H |  | YES | YES | GET API
2 | Create/Register End points for GET API
3 | Create/Build method for GET API
4 | Register all custom field within new Video content type
5 | Enquee Endpoints within WP Default - wp-json/wp/v2/types
6 | Create GET API & Expose all fields data
7 | Authenticate API via App Password
8 | Create Scema / Format JSON Response & consume API
1 | Create/Register End points for POST API | 32H |  | YES | YES | POST API
2 | Create/Build method for POST API
3 | Send request for Create post with rquired field arguments
4 | Validate required field data
5 | Validate Headers/Body
6 | Save request & processed data in Database
7 | Authenticate Request by using app password
8 | Authenticate API via App Password
| Handling Server Error/Response | 8H
Initialised Server CurL
Application Password Configuration - need to be check with API